## OVERVIEW
Lake Superior State University
Charter Schools Office
Continous Improvement Plan (2021-2025)
Mission: To ensure quality oversight and support to our authorized charter academies resulting in students who are prepared for the next phase of life whether it be attending college or entering the work force.
Core Values
| Excellence in Teaching and Learning | Our first priority is high quality instruction and positive educational outcomes. We focus on building relationships that promote academic excellence.
| Opportunity | The students and staff that are affiliated with LSSU CSO authorized academies have access to a wide range of opportunities to grow academically, professionally, culturally, and socially.
| Accountability | We believe in holding our stakeholders and overselves accountable for the results of decisions and actions that influence performance.
| Diversity | We recognize the uniqueness of individuals, academies, and communities. Their diverse perspectives and experiences enrich the educational experience for all stakeholders.
| Ethics and Values | The LSSU CSO promotes an environment of transparency, honesty, respectful and courteous behavior where everyone is valued and empowered.
| Stewardship | The LSSU CSO intentionally operates in a sustainable way in order to leave our academies sound for future generations of charter students, alumni and friends.
| Glossary of Terms | District Target Tier |  |  | Overarching Goals
|  | Tier 1 | All Districts | For Goals 1 & 2: See flow chart per category for determining tier placement. | 1 | Improve academic achievements of the LSSU Charter Schools Office portfolio.
|  | Tier 2 | Some districts that are in need of increased support to be successful. |  | 2 | Improve academy proficiency and competency in operational areas.
|  | Tier 3 | Few districts that are in need of intense support to be successful. |  | 3 | Increase positive interactions and contacts between LSSU and all LSSU chartered academies.
[5 empty] | 4 | Increase stakeholder exposure to the LSSU CSO mission, vision, and direction.
|  | Student Target Tier |  |  | 5 | Complete the accreditation process.
|  | Tier 1 | All students |  | 6 | Develop collective capacity and knowledge.
|  | Tier 2 | Students who have deomonstrated increased need for support to be successful.
|  | Tier 3 | Students who have demonstrated need for intense support to be successful.
Phase
|  | Getting Ready I | Strategy for implementation is researched as to the best way to address challenges indentified in the needs assessment and preparations made on how to best implement, monitor, and evaluate said strategy.
|  | Implementing II | Selected strategy is put in place and carried out as per the getting ready plan for a set period of time.
|  | Monitoring III | After stated period of time, predetermined data is collected on strategy to be reviewed for evaluation purposes.
|  | Evaluating IV | Analyzing and using collected data answer questions about programs and practices, particularly about their effectiveness and efficiency in producing an intended effect. Evaluation includes the analysis of implementation and achievement results.
Note on A1: ====== ID#AAAAGdPRh80 Brooke Maciag (2020-04-30 03:14:54) Still working on formating and cleaning things up a bit, but this will give you a gist of the overall document.

## GOAL ONE
Area of Concentration |  | Strategy |  | District Tier | Student Tier | Phase | Point Person | Resources Needed | Progress Indicators/Data Used for Progress Evaluation | Progress Evaluation/ Notes (Including how & when will we evaluate?) | Going Forward | Priority Year | Target Date
Goal 1: | Improve academic achievements of the LSSU Charter Schools Office portfolio.
COVID 19 Response Adaptation |  | 1 | Procure and maintain an online learning platform for professional development sessions. | I | N/A | Monitoring | Brooke Maciag & Julie Hopper | Work with online platform company and LSSU Tech and Theater departments to implement | Participation in sessions, session reviews, on demand views | Brooke needs to work with On24 to create a PD HUB on our homepage, create PD calendar by June 30th | Created PD calendar by June 30th 7/12/21- solidify dates | 21-22 | 2021-07-30
Reading/ Lang Arts |  | 2 | EDUC 624- Reading and Research Methodology | I | II, III | Evaluate | Julie Hopper | This course is in collaboration with LSSU Department of Education. | LSSU authorized academies will demonstrate a need for the course as evidenced by participation rates in the course. | Participation/Follow Up/Satisfaction Survey needs to be developed. We need to check that that doing this survey is not in violation of the faculty contract. | Get in touch with Barb and get a processess set up that for the LSSU CSO students to complete. Focus is CONTENT not instuction since we cover the tuition of these students. 7/12/21- Separate eval on content to determine when and if we are going to offer again | 21-22
General Instruction |  | 3 | Provide Professional Development Sessions for Tier One Instuctional Best Practices: Executive Functioning as Tier One in the School System (Individual and Teams), Virtual Learning, High Leverage Instructional Practices, and Inquiry Based Instruction | I | I | Getting Ready | Brooke Maciag | This session will be available to all schools. Locations and dates will need to be established, and will be worked out in the Educational Leadership workgroup. Schools will send teams to this and admins will recieve a Gold Standard of Implementation for this training to be able to monitor proper installation within the classrooms. | Implementation Guide Feedback, Survey data | As a result of Covid restrictions recently being lifted, we are again planning professional developments. Create PD Calendar, PD Presentations, and Implementation Guides | Create PD Sessions and calendar- 7/12/21- 3 year rough plan created, working on locking in dates | 21-22 | 2021-07-30
|  | 4 | Work with Michigan Council for the Social Studies to provide professional development on implementing and teaching new SS Standards. | I | I | Getting Ready | Brooke Maciag | Michigan Council for Social Studies Membership | M-step comparison data to geographically and demographically like districts | Brooke has joined MCSS and is currently on the ballott for the vacant Board of Directors seat as a Upper Peninsula Representative. Access to this council will put us in the loop of available PD and curriculum developments that will be passed along to LSSU CSO schools. | Get results of election and attend meetings, get with Dave Johnson to see what is available now to transition to new standards. 7/12/21- Election results in, Brooke sitting at District 1 representative, attend retreat on July 20 | 21-22 | 2021-07-20
|  | 5 | Create a Multi-Step Tiering (Categorizing method) - Focused support based on identified needs in the area of Academics | I | N/A | Implementing | Brooke Maciag | Academic Rubric and Portfolio Report | Rubrics will be filled in based on the timeline provided in the MTSS handbook. | Our first runthrough of implementation will be in the 2021/22 school year. Rubrics for Academics will be completed and plans established before October 2021. | Compile rubrics, timelines, and plan templates into an SOS Handbook 7/12/21- DONE, ready for printing and distribution. Do an ON24 explaining it. 9/19/21- Reviewed system and decided a name change for clarification would be needed. Named of program changed to System of Support to be deemed as SOS going forward. In do this the team also reviewed terminology within the manual and made some changes. An overview webinar will be created before academies are notified of the TIER rating, and plans for support are created and implemented. | 21-22 | 2021-07-30
|  | 6 | Create a plan of support for tiers II and III of MTSS in the areas of Finance | I | N/A | Implementing | Brooke Maciag | Tiering Support for Academic Rubric
|  | 7 | Continue to create a yearly LSSU CSO PD Catalog that is available for public viewing | I | I | Monitoring | Brooke Maciag | PD Calendar and session descriptions, ON24 platform, LSSU Webmaster | Track touches on WebPage, attendance | Website touches will be tracked and reviewed and attendance to PD sessions will be reviewed quarterly at minimum. Catelog will be completed by July 30th for the 2021. | Complete catalog and figure out how to link ON24 into those sessions. 7/12/21- One pager complete, working on specific dates and individual one pagers for registration | 21-22 | July/ Aug
|  | 8 | Identified Districts- Support of Blueprint Installation at identified Partner Districts and Targeted Support Schools. | III | III | Evaluate | Brooke Maciag | Due to their identification as a partnership district, both MDE and LSSU CSO are in support of SJW, MMA, and AIA installing the Blueprint with the SWFT Due to their inclusion on the TSI schools list in the area of special education, both MDE and LSSU CSO are in support of DSLA installing the Blueprint with the SWFT. Brooke is to start sitting in BP meetings. | Blueprint indicators, LSSU Satisfaction of Blueprint Survey | Schools will be removed from Priority and Targeted lists at the end of the 2021/2022 SY, evaluations will be conducted, and based on Index scores of 2022, schools will be re-identified. Brooke currently attends OCAMT Blueprint/Partnership Meetings and provides feedback to Chris. | Continue to attend meetings 7/12/21- Get 21/22 Calendar of meetings and attend | 21-22 | July/ August
Special Education |  | A | PD; Legal Updates & Best Practices- Child Find Process | I | I | Getting Ready- On hold as a result of Covid 19 pandemic | Brooke Maciag | Brooke needs to maintain membership in MAASE and attend MAASE meetings to better develop her own knowledge base in this area. Additionally, data needs to be gathered as to current child find processess that are being implemented and analyised for consistent areas of concern. Potentially tag up with GVSU and other authorizers around the state to offer this PD. | On hold until we understand what our role/approach/platform will be for the 20/21 school year.
|  | 9 | Special Education/504 Workgroup for Best Practices | I | II, III | Getting Ready | Brooke Maciag | Access to SpEd staff emails to create mailing list, Access to Trinere Powell to help create this group and get it off the ground until we are able to secure SpEd support from the School of Education. Must work with Becky to create a budget to provide compensation for leading the group. | Attendance and participation takeaways | This was just getting off the ground when COVID hit and was called off once schools settled into their virtual learning routines. Contact Trienere and see if she is willing to take point on this relaunch project with support from LSSU CSO | 7/12/21- Discussion with Angela Nettleton to head this and oversee it. Planning meeting scheduled for July. | 21-22 | July/ August
|  | 10 | Work with GVSU, SVSU, and LSSU School of Education to create a sustainable SPED monitoring tool and process. | III | III | Getting Ready | Brooke Maciag | School of Education support, access to SVSU and GVSU's tools and support and inquire for job description from Cindy Shinsky from GVSU to potentially create a similar roll in the LSSU CSO office. | Creatation of Monitoring Tools and information gleaned from Monitoring Audit. | Inquire about cost to office, Cindy's job description for her SVSU postion, and secure support for LSSU CSO's. Create tools in 2021/2022 and implement monitoring by 2022/23. | set meeting with Barb Light to discuss postion, set meeting with Cindy Shinsky and Chris and Brooke to discuss her role at SVSU. | 21-22 | August
Whole Child- WSCC Model |  | 11 | PD; Adverse Childhood Experiences and Trauma Informed Classrooms | I | II, III | Implementing | Julie Hopper | Julie needs to continue to attend the ACE conference each year and work with Oakland University to bring these sessions to districts as needed. | ACE follow up survey | These professional developments also need to be available for LSSU CSO staff to deepen our understanding of the different models/approaches of Whole Child Education. | add sessions into PD calendar 7/12/21- Set up trainign for CSO staff, add to retreat agenda? | 21-22 | Retreat dates
|  | 12 | PD; CPI Training for Academy | I | II, III | Implementing | Brooke Maciag | Brooke will need to maintain certification for CPI training that takes place every three years. These sessions are on an as requested basis and available for all districts. Brooke needs access to CPI's training sessions to master the instructional techniques that coincide with the new TEXT book. | Behavior data from schools, session evaluations | CPI Certification test result. This year we're going back face to face in some locations for this. | add sessions into PD calendar, schedule summer training session for LSSU CSO schools and attend training the trainer session this summer. | 21-22 | July-September
|  | 13 | EDUC 400- Trauma Informed Instruction | I | II, III | Implementing | Julie Hopper | This course is in collaboration with LSSU Department of Education. Barb Light, Cathy White | LSSU authorized academies will demonstrate a need for the course as evidenced by participation rates in the course. | Move to evaluation in August 2021 | 7/12/21- Need calendar, evaluation of content (ask Barb) | 21-22
|  | 14 | Create a Multi-Step Tiering (Categorizing method) - Focused support based on identified needs in the area of Whole Child | I | N/A | Implementing | Julie Hopper & Field Reps | Tiering support for Whole Child Rubric | Scoring of Whole Child Tiering Rubric | Our first runthrough of implementation will be in the 2021/22 school year. Rubrics for Academics will be completed and plans established before October 2021. Need to train Field reps on how to create plans. | 7/12/21- Coordinate Field rep trainnig on tiering/plans | 21-22 | Retreat dates
|  | 15 | Create a system of support for tiers II and III of MTSS in the areas of Whole Child | I | N/A | Implementing | Julie Hopper & Field Reps | Tiering support for Whole Child Rubric & PD opportunities, use tool for plan development | Scoring of Whole Child Tiering Rubric & PD attendance

## GOAL TWO
Area of Concentration |  | Strategy |  | District Tier | Phase | Point Person | Resources Needed | Progress Indicators/Data Used for Progress Evaluation | Progress Evaluation/ Notes (Including how & when will we evaluate?) | Going Forward | Priority Year | Target Date
Goal 2: | Improve academy proficiency and competency in operational areas.
Governance & Compliance |  | 1 | Provide Professional Development Sessions targeting topics that arise from Field Rep reports, review of minutes, and additional concerns | I | Evaluate | Chris Oshelski & Jenny Peterman & Becky Clawson | Angie Irwin, MDE, Dykema & other consultants | Field Rep notes of improvement in meeting performance, PD attendance logs, Open Meeting Act violations | How: Epicenter compliance ratings have improved, field reps are seeing less open meetings act violations, and webinars are being referenced in board meeting minutes. When: Review in summer for planning for next year. | Continue strategy 7/12/21 Angi- New Series, 101 Board Orientation, ON24 videos | 21-22
|  | 2 | Continue to ensure charter contracts include updated applicable law | I | Evaluate | Chris Oshelski & Jenny Peterman | MDE, Dykema, Revised School Code & Reauthorization process | Board approval of revised T&C | Reviewed at contract expiration or prior if large changed are needed in T&C | Continue strategy 7/12/21 Jenny heading up reauths | 21-22
|  | 3 | Create a Multi-Step Tiering (Categorizing method) - Focused support based on identified needs in the area of G&C | I | Implementing | Chris Oshelski | Tiering support for Governance & Compliance Rubric | Scoring of G&C Tiering Rubric | Our first completion will occur after G&C reports are complete. Rubrics will be completed by August/September and tiering will follow. Academy improvement plans will be completed according to cycle outline in MTSS document. | Do first round of this | 21-22 | September/October
|  | 4 | Create a system of support for tiers II and III of MTSS in the areas of G&C | I | Implementing | Chris Oshelski & Field Rep | Tiering support for G&C Rubric & PD opportunities, use tool for plan development | Scoring of G&C Tiering Rubric & PD attendance | Tool for plan development is created, field reps need to be trained in the tool after identification is complete. 9/19/21- Reviewed system and decided a name change for clarification would be needed. Named of program changed to System of Support to be deemed as SOS going forward. In do this the team also reviewed terminology within the manual and made some changes. An overview webinar will be created before academies are notified of the TIER rating, and plans for support are created and implemented. | Do first round of this | 21-22 | September/October
|  | 5 | Continue to provide School Districts with individualized annual reports depicting trend and performance data in the areas of G&C | I | Evaluate | Chris Oshelski | Board attendance log, Board minutes, QPR reports, Hylant report, ReCon report, & MDE communications, Field Rep input | Board minutes are noting changes based on report findings, field reps are seeing changes in how board operate based on report feedback | Every August reports will be completed. These reports will be used to complete rubrics for MTSS, and plans will be developed to address areas of weakness. | Tie to reports to rubric for plan for board improvements | 21-22 Ongoing | August/ September
|  | 6 | Continue to provide a Field Officer that attends each board meeting and provides guidance as needed | I | Embedded | Chris Oshelski | Field Representative positions, Field Rep Reports | Field Rep attendance logs & reports | Strategy has become basic operating procedure. | Continue strategy
Finance |  | 7 | Create a Multi-Step Tiering (Categorizing method) - Focused support based on identified needs in the area of Finance | I | Implementing | Becky Clawson | Annual Financial Rubric & Reports | Annual Financial Rubric & Reports | Our first completion will occur after Finance reports are complete. Rubrics will be completed by November/December and tiering will follow. Academy improvement plans will be completed according to cycle outline in MTSS document. | Do first round of this | 21-22 | December 2021
|  | 8 | Create a system of support for tiers II and III of MTSS in the areas of Finance | I | Implementing | Becky Clawson | Tiering Support for Finance Rubric | Scoring of the Finance Rubric | Tool for plan development is created, all staff need to be trained in the tool after identification is complete. 9/19/21- Reviewed system and decided a name change for clarification would be needed. Named of program changed to System of Support to be deemed as SOS going forward. In do this the team also reviewed terminology within the manual and made some changes. An overview webinar will be created before academies are notified of the TIER rating, and plans for support are created and implemented. | Do first round of this | 21-22 | December 2021
|  | 9 | Continue to provide School Districts with individualized annual reports depicting trend and performance data in the areas of finance | I | Evaluate | Becky Clawson | Annual Audited Fin Statements, Audited pupil counts, Epicenter Submissions | Annual Financial Rubric & Reports | Every December reports will be completed. These reports will be used to complete rubrics for MTSS, and plans will be developed to address areas of weakness. | Use annual reports to score for plan for board improvements | 21-22 | December 2021
|  | 10 | Continue to provide a Field Officer that attends each board meeting and provides guidance as needed | I | Embedded | Becky Clawson | Budget for Field Representative positions | Sufficient number of Field Reps | Strategy has become basic operating procedure. | Continue strategy | Ongoing | December 2021

## GOAL THREE
Area of Concentration |  | Strategy |  | District Tier | Student Tier | Phase | Point Person | Resources Needed | Progress Indicators/Data Used for Progress Evaluation | Progress Evaluation/ Notes (Including how & when will we evaluate?) | Going Forward | Priority Year | Target Date
Goal 3: | Increase positive interactions and contacts between LSSU and all LSSU chartered academies.
Enrollment & Retention |  | 1 | EDUC 624- Reading Interventions, reduced enrollment fees for educators working for our academies | I | II, III | Monitor | Julie Hopper | CSO to work with Admissions office, Dean of School of Education, and Registrars Office | Enrollment #'s in course, Conversations with the Dean re: course satisfaction reports | Participation/Follow Up/Satisfaction Survey needs to be developed. We need to check that that doing this survey is not in violation of the faculty contract. | Get in touch with Barb and get a processess set up that for the LSSU CSO students to complete. Focus is CONTENT not instuction since we cover the tuition of these students. | 21-22 | yesterday?
|  | 2 | Communications & Support packages of former LSSU Charter School Students who currently attend LSSU | N/A | N/A | Implementing | Chris Oshelski & Jenny Peterman | Connections with Admissions and Financial Aid, Student life office/Admissions for lists of students and how to contact. | # of students who take advantage of the packages | COVID made this hard. We plan to execute in 2021/22 and then evaluate. | Continue Fall/Spring | 21-22
|  | 3 | Junior Laker Scholarship | I | I | Monitor | Chris Oshelski | Financial Aid, Admissions, ARGOS report | # of students receiving the scholarship | Dashboard #'s from conversation had w/ admissions and are promoting more. | Coordinate meeting with admissions and HS academy leaders to offer acceptance letters to all seniors that attend one of our academies. 7-12-21: Rebranding with Admissions & Financial Aid | 21-22
|  | 4 | EDUC 400- Trauma Informed Practices | I | II, III | Getting Ready | Brooke Maciag, Cathy White, Chris Oshelski, Barb Light | Work with School of Education to create course, business and registrars office to get it ready for roll out | LSSU authorized academies will demonstrate a need for the course as evidenced by participation rates in the course. | Move to evaluation in August 2021
Outreach |  | 5 | Campus and community 3% Grants | I | I | Monitor | Chris Oshelski & Jenny Peterman | Application, Provost approval, Tracking spreadsheet | Tracking spreadsheet, Expenditure tracking worksheet | Pandemic slowed applications but we expect it to increase #'s in the fall of 2021/22 | Continue | 21-22
|  | 6 | Traveling Educational Programs staffed by LSSU Staff & Faculty | I | I | Implementing | Chris Oshelski, Jenny Peterman, & Field Reps | Application, Provost approval, Tracking spreadsheet, CFRE resources, Admissions, CFRE | Participation logs from LSSU staff & faculty, summary reports are provided to LSSU CSO from each event | Between Pandemic and new LSSU staff we found we need to do a better job documenting the process so incoming staff have a better idea of opportunities | Create instruction manual on opportunities, expectations, and documentation requirements that are needed. 7/12/21 Process has been created
|  | 7 | LSSU CSO Summer Retreat- Networking events | I | I | Monitor | Chris Oshelski, Brooke Maciag, & Jenny Peterman | Budget, PD presenters, campus community & city resources | attendance and evaluations | Working with SVSU to create an Administrators Camp for school administration leaders for both authorizers. Then thinking of doing the same with yearly board camps |  | 22-23
|  | 8 | Leadership Camp | I | I | Monitor | Chris Oshelski | Admissions will partner with CSO to create camp opportunities. | attendance, evaluations, & expenditure tracking | On hold from Pandemic. | Start planning for 2022
|  | 9 | STEAM Camp | I | I | Monitor | Chris Oshelski | Admissions will partner with CSO to create camp opportunities. | attendance, evaluations, & expenditure tracking | On hold from Pandemic. | Start planning for 2022
|  | 10 | Individual Academy Camps | I | I | Monitor | Chris Oshelski | Admissions will partner with CSO to create camp opportunities. | attendance, evaluations, & expenditure tracking | On hold from Pandemic. | Start planning for 2022
|  | 11 | Sports Team visits to academies | I | I | Monitor | Chris Oshelski | Application, Provost approval, Coach approval, LSSU Athletic Director | attendance, email & expenditure tracking | Tabled b/c of COVID new AD, we need to set up a meet with him | Create process so new AD can pass on to new coaches and ask AD to review options w/coaches once a year. 7-12-21 Process created; NEW AD | 21-22 22/23
|  | 12 | January Board Recognition | I | I | Getting Ready | Chris Oshelski, Jenny Peterman, & Field Reps | Budget, Field rep attendance | Field rep Reports & board minutes | Revisit our whole system and overhaul | Revisit in Aug/September when we meet with field reps
|  | 13 | Site visits by LSSU CSO Staff | I | I | Monitor | All LSSU CSO Staff | Travel approval & site visit reports | Epicenter site visit reports & Travel Vouchers | On hold from Pandemic. | Continue | 21-22 | 9/21
LSSU Department of Education Students |  | 14 | Work with LSSU Department of Education to place student teachers in LSSU Academies |  |  | Getting Ready | Brooke Maciag | Work with LSSU Department of Ed and academies to facilitate connections, Cathy White, Barb Light, Chris Oshelski | #/% of placements | Trying to set up a 2 day field trip to urban schools for field work | Set up meeting with Barb, Cathy, Brooke, and Chris for June to see if this can take place for Fall21
|  | 15 | Work with LSSU Department of Education to increase number of graduated teachers in LSSU Academies |  |  | Getting Ready | Brooke Maciag, Cathy White, Chris Oshelski, Barb Light | Work with LSSU Department of Ed and academies to facilitate connections | #/% of placements | Have been using LSSU authorized academies for mock interviews for student teacher course | Need to get statistics from School of Education

## GOAL FOUR
Area of Concentration |  | Strategy |  | Phase | Point Person | Resources Needed | Progress Indicators/Data Used for Progress Evaluation | Progress Evaluation/ Notes (Including how & when will we evaluate?) | Going Forward | Priority Year | Target Date
Goal 4: | Increase stakeholder exposure to the LSSU CSO mission, vision, and direction.
National |  | 1 | Attend and work toward presentation opportunities at NACSA to continue networking with other academies, authorizers, state charter organizations, and legislative lobbyists | Monitoring | Chris Oshelski | Attendance for core team, move toward presenting our story at NACSA | NACSA Agendas & information | Chris presented at the 2020 NACSA Meeting, meetings are held annually, Pandemic has changed attendance, hope to return to F2F meetings in the future | Continue to attend | 22-23
|  | 2 | Attend Higher Education Institutions meetings to work/network with and learn from higher educational authorizers from around the country. | Monitoring | Chris Oshelski & Brooke | Attendance and participation in meetings throughout the year around the country. | HEI Agendas & information | Meetings have been sporatic and virutal due to the pandemic. | Continue to attend | 22-23
State |  | 3 | Continue to maintain active membership in Michigan Council of Charter School Authorizers | Embedded | Chris Oshelski | Attendance & participation | Agendas and Minutes | Monthy meetings have shifted to virutal due to pandemic. Attendance from LSSU CSO has been consistent. Chris currently holds the office of VP of the Council. | Continue to attend | 21-22 ONGOING
|  | 4 | Continue participation in MCCSA subgroups; Finance, Academic, Governance, and Special Education | Embedded | Jenny Peterman, Becky Clawson, Julie Hopper, & Brooke Maciag | Attendance & participation | Agendas and Minutes | Finance: Quarterly, however sporatic due to pandemic. Governance: Quarterly Academic: Quarterly (Julie currently is leading this group) SpED: Meets monthly | Continue to attend Finance: Pandemic Impact # of meetings? Should have a new schedule for 21-22 | 21-22 ONGOING
|  | 5 | General attendance at MAPSA Symposiums | Embedded | Chris Oshelski | Attendance & participation | Agendas and information | 2020 Virutal meetings were held over a period of months, LSSU CSO continues to sponsor | ;
|  | 6 | Present at MAPSA Symposium to create networking opportunites and share point of view | Monitoring | Julie Hopper | Work with MAPSA to idenity topics of need | Julie presented ACES, Madeline Black presented | Revisit closer to MAPSA meeting | Reach out to Becky Carlson at MAPSA and see how we can be a bigger presence at Symposium
|  | 7 | Sit on MDE committees when opportunities arise. | Monitoring | Brooke Maciag | Keeping in contact with MDE to be connected when opportunities arise. | Sat on Appropriate Placement in 19/20 | Continue
|  | 8 | Belong to and participate in other State Organizations; MASSP, MEMSPA, MAASE, MICPA, MSBO | Evaluating | Brooke Maciag & Becky Clawson | MSBO Certification Track, Annual Dues | Subscriptions & Certifications | Returing to normal routines for 21/22 school year. MSBO cert- on hold from pandemic | update memberships before July 30, 2021
|  | 9 | Charter School Day at Capitol Building | Embedded | Chris Oshelski & Jenny Peterman | Participation & Sponsorship | Participation & Sponsorship items | Someone from our office is always in attendance, some of our academies are involved and we're creating our own virtual CSW. 2021 attendance was affected by pandemic | sponsorship & Attendance | 21-22
Local (LSSU, EUPISD, etc.) |  | 10 | Chamber of Commerce Presentations about Charter Schools | Monitoring | Chris Oshelski & Julie Hopper | Presentation & Charter School Information | Yearly Participation & Agendas | Leadership program postponed due to pandemic, will resume soon | Stay available
|  | 11 | Create, review, and monitor CSO Admin Budget both annually and quarterly | Embedded | Becky Clawson | Itemized budget, staff input & forecasting | Submit budget to VP of Finance & periodically review | Meet quartely to discuss current year budget, and meet in Spring to create upcoming year budget | Continue strategy | ongoing | ongoing
|  | 12 | Compile and disseminate attendance data for LSSU CSO students in Concurrent Enrollment, Dual Enrollment, and Early Middle College programs | Monitoring | Chris Oshelski & Molly Mande | CE/DE position & information | Participation for CE/DE/MC | We need to move toward evaluating this strategy, based on how many students of ours attend these programs. Pandemic pushed this timeline. | Revist evaluation of LSSU CSO student attendance at end of SY 2022
|  | 13 | Create and maintain LSSU CSO Job Manuals | Monitoring | Chris Oshelski | Staff input & Google docs | Updating job descriptions | Office reorganization and pandemic have altered duties and timelines. Move to evaluation July/September 2022 | Push to revisit these during the 2021/2022 school year. 7/12: Jenny/Becky Reorg | 21-22
|  | 14 | Maintain LSSU social media pages | Monitoring | Brooke Maciag, Julie Hopper, |  | yearly review of analytic data from social media platforms | Create a social media plan for 2021/2022 school year. | Create a calender based on monthy themes?? Assign CSO Staff/ weeks | 21-22 | September 21 at implementation
District |  | 15 | Board and Administrator Retreat Hosted @ LSSU every three years | Monitoring | Chris Oshelski & Jenny Peterman | PD consultants & Campus Resources | Participation & Surveys | Plan to host July 2022 at LSSU, may need to utilize ON24 to mitigate expenses
|  | 16 | Portfolio Reports | Evaluating | Julie Hopper | Dr. Lance- We don't have the capacity to create the reports on our own based on the extensive coding that goes into them. | Stakeholders Survey | Tie into perception survey: Do you feel you accurately informed by LSSU CSO of your school overall performance? | Create perception survey. 7/12/21 200+ participants
|  | 17 | Quarterly Newsletter | Embedded | Julie Hopper |  | Perception Survey | Articles are based on current LSSU operations and upcoming events we are offering, highlighting district??????, | Create perception survey. 7/12/21 200+ participants
|  | 18 | Annual Reports for Academics, Finance, and Compliance & Governance | Embedded | Chris Oshelski, Jenny Peterman, Becky Clawson, & Julie Hopper | Data & Info needed for each report | Reports presented to each academy & recorded in board minutes | Utilized as base for MTSS and reauthorization | Continue strategy | 21-22 ONgoing
|  | 19 | Presentation of Annual Reports at Local District Board Meetings | Monitoring | Chris Oshelski, Julie Hopper & Field Reps | Annual Reports & CSO staff participation | Reports presented to each academy & recorded in board minutes | Need to work on being consistent for process on sharing reports with districts. | Create a consistent process and implement 7/12/21 Process created (share) | 21-22 ONgoing

## GOAL FIVE
Area of Concentration |  | Strategy |  | Phase | Point Person | Resources Needed | Progress Indicators/Data Used for Progress Evaluation | Progress Evaluation/ Notes (Including how & when will we evaluate?) | Going Forward | Priority Year | Target Date
Goal 5: | LSSU will complete the accrediation process.
Strategic Action Plan |  | 1 | Gather input and create one document for plan, that can be shared with others. | Implementing | Chris Oshelski & Brooke Maciag | Zoom, Staff Meetings, Surveys, Cindy | SAP Document, Staff agendas, Agenda notes, changes marked on plan with dates following evaluations, CIP | Calendar needs to be created to establish schedule for coming back to plan frequently to make Continuous Improvement part of our office culture. | Create calendar with Chris (per goal) Calendar for quarterly meetings (Goals) | 21-22 | 2021-09-21
Complete Authorizer Accreditation Process |  | 2 | Reauthorization process | Evaluating | Chris Oshelski | Epicenter, Dykema, & Reauthorization Packet | Reauthorization process/ application/ rubrics | Completed one whole cycle with Dykema and all of acadmies have consistent contracts |  | 21-22 | September/October
|  | 3 | Complete MDE Assurances and Verifications | Embedded | Chris Oshelski & Jenny Peterman | Documentation for MDE A&V Google folders | MDE letter of completion | Done | COMPLETED
|  | 4 | Complete MCCSA Assurances | Embedded | Chris Oshelski & Jenny Peterman | Documentation for MCCSA assurances & Google folders | MCCSA letter of completion | Done | COMPLETED

## GOAL SIX
Area of Concentration |  | Strategy |  | District Tier | Phase | Point Person | Resources Needed | Progress Indicators/Data Used for Progress Evaluation | Progress Evaluation/ Notes (Including how & when will we evaluate?) | Going Forward/ Notes | Priority Year | Target Date
Goal 6: | Develop collective capacity and knowledge of the LSSU Trustees, Academy Boards of Education, and LSSU CSO staff.
Local- LSSU BOE |  | 1 | Provide full charter contracts to LSSU Board of Directors to have access to ESP, lease, and other agreements within the contracts |  | Embedded | Chris Oshelski & Jenny Peterman | Contracts & Dykema services | LSSU Board approval of contracts |  | Continue Strategy | 21-22
|  | 2 | Provide full partnership contracts to LSSU Board of Directors to have access to the goals set forth and areas of concern |  | Monitoring | Chris Oshelski & Jenny Peterman | Contracts & Dykema services | LSSU Board Approval of Contracts | Chris presents partnership contracts at board committee meetings and answers any questions board members may have | Continue Strategy | 21-22
|  | 3 | Yearly Academic Report presented to LSSU Board |  | Embedded | Julie Hopper | Dr. Lance's reports |  | Julie usually presents at the November board meeting however did not in 2020 because of the pandemic. Will resume in 2021 in some form. | Work with Provost and Director on what will be presented at the 2021 meeting | 21-22 | 11/21
|  | 4 | Continue to provide yearly updates on charter schools office meets LSSU Strategic Action Plan |  | Implementing | Chris Oshelski | Data from departments | Provost and President provide feedback to director | Plan adopted just prior to pandemic shut down. Will be reviewed at September annual meeting | Continue and revisit after September 2021
|  | 5 | Present dashboard updates to LSSU Board during their scheduled board meetings. |  | Embedded | Chris Oshelski | LSSU Agenda | LSSU Board meeting minutes | Feedback from Provost | Continue BOT Meetings | 21-22
|  | 6 | Provide updates to Provost during monthly meetings. |  | Embedded | Chris Oshelski | Provost agenda items | Provost agenda & notes | Evaluation? (could this be a data point for Chris to use in his eval?) | define how it will be measured
District- Academy |  | 7 | Provide professional development for academy boards on how the MTSS process (rubrics, tiers, plans) works. | I | Getting Ready | Brooke Maciag | Annual report information to Tier Academies MTSS handbook | End of webinar survey, field rep notes if conversation appears in agendas | This will need to be in place soon, and then marketed to boards as a Live then Live On Demand webinar. (Can also be targeted at school leaders and ESP's.) | Put together MTSS handbook, put together PD.
|  | 8 | Continue Airwin Webinar sessions | I | Embedded | Chris Oshelski & Jenny Peterman | Angie Irwin & Field Rep Board Topics | Attendance Logs & Academy Board minutes | Attendance, takeaways, participation stats, application of topics in board practices Review data and plan yearly based on Field Rep observation and the Tiering/Reports Schedule meeting with field reps to collect input on effectiveness of previous years sessions and concerns to be addressed in the upcoming year. This meeting should take place prior to meeting with Airwin to plan for the next year's sessions. | Set date and agenda for Director, Jenny, and Field Rep meeting to review and plan. | 21-22 | 8/21
|  | 9 | Continue with legal professional development sessions | I | Implementing | Chris Oshelski & Jenny Peterman | Dykema & Legal topic suggestions | Attendance Logs & Academy Board minutes | During the pandemic this is one of the approaches that got dropped. We would like to bring it back on a regular basis. We need to work with Dykema to establish topics and dates. | Chris & Jenny work with Dykema to create PD plan. | 22-23
|  | 10 | Board Pres/VP Round Tables | I | Getting Ready | Chris, Jenny Peterman & Field Reps | Virtual Platform & Topics/Info/Issues | Attendance Logs | This was something we wanted to roll out in 2020/21 but was pushed on account of the pandemic. We would like to work to put it in place for the start of the 2021/22 school year. | Determine who will be in charge of this and who will attend, and how often they will meet and who will create agendas. 7/13/2021- Push until 2022/23 | 22-23
|  | 11 | ACE Training for Academy Boards |  | Implementing | Julie Hopper | ON24, academy emails, field reps to propose at board meetings | Topics are discussed in board meetings, School leaders feel more supported, Field Reps notes should show boards are integrating the PD into their own board and school culture. | These sessions need to be recorded via ON24 and then marketed) targeting school boards. | Julie needs to put together an ON24 presentation, Brooke creates the ON24 webinar, session needs to be targeted at board members. | COMPLETED
|  | 12 | Continue 3 year cycle for Summer Retreat | i | Implementing | Chris Oshelski & Jenny Peterman | PD Resources, LSSU Campus Resources, & CSO Staff | Attendance & Surveys | Review Surveys from last session, collect topics of interest for next session. | Revisit this standard in September of 2021. | 22-23
|  | 13 | Open Meetings Act Materials provided to each board member | I | Monitoring | Chris Oshelski & Jenny Peterman & Field Reps | OMA Manual & Field Rep Guidance | Board minutes & OMA violations | Board Gears & Webinars | Create plan to formalize/regulate at field rep meeting in August/September | 21-22 | 9/21
|  | 14 | Board Gears online learning modules | I | Monitoring | Field Reps | LSSU CSO website & CMU Board Gears | Attendance & PD Board Logs | We currently have no way to monitor who views these if they are doing so independantly. | Explore if we can create an ON24 webinar that incorporates the board gears as they are.
|  | 15 | Annual Reports; Academic, Financial, Governance and Compliance | I | Implementing/Monitor | Chris Oshelski, Jenny Peterman, and Becky Clawson | Annual reports information, ON24, Brooke Maciag | Reports presented at Board meetings & minutes | waiting until next rounds of reports are complete to release ON24 webinars on how to read the reports to the board members | Create ON24 webinars- G&C | 21-22
Local- LSSU CSO |  | 16 | Remain ACE, CPI, and certified |  | Embedded | Julie Hopper & Brooke Maciag, | funds to allow for continued training and certification and time to attend training sessions | ????
|  | 17 | Remain CPA certified |  | Embedded | Becky Clawson | funds to allow for contined training and certification and time to attend training sessions | CPE Hours earned & Liscense renewal (Bi-Annually) | Annually 40 hourse of CPE req'd | Continue Strategy | ongoing | ongoing
|  | 18 | NACSA | I | Embedded | Chris Oshelski | Membership Dues | Participation for Annual Conference, Individual Evaluations or PD plans. Data | Individual learning plans for staff members | Create/integrat this into the evaluation system already in place | ongoing
|  | 19 | MAPSA | I | Embedded | Chris Oshelski | Membership Dues & Sponsorships | Participation for Annual Conference, Individual Evaluations or PD plans. Data | Individual learning plans for staff members | Create/integrat this into the evaluation system already in place | ongoing
|  | 20 | MCCSA Professional Groups | I | Embedded | Jenny Peterman, Becky Clawson, Julie Hopper, & Brooke Maciag | Membership and Meeting participation | Meeting Minutes and reporting back at staff/leadership meetings on meeting highlights. | Need to complete the cycle of information and debrief rest of CSO staff with updates from the meeting | Formalize follow up process 7/12/21- Finance; pandemic Impacted # of meetings. Should be back on track 2021-22
|  | 21 | MAASE, MEMSPA, MCSS, MASSP |  | Implement | Brooke Maciag | Time and budget to attend sessions and meetings and stay a member | Content implemented into Leadership Meetings and PD's. | Stay a member | Pay membership dues by June 30th, 2021
|  | 22 | Trauma Sensitive Classroom and Instruction |  | Monitoring | Julie Hopper |  |  |  | Create ON24 webinars | 21-22 | 9/21
|  | 23 | Staff Meetings | N/A | Embedded | Chris Oshelski & Jenny Peterman | Virtual Platform & Topics/Info/Issues | Agenda, minutes & participation | Face to face meetings two/three times a year and monthly via virtual platform. | Formalize follow up process
|  | 24 | Individualized Learning Paths for LSSU CSO Staff based on evaluation process | N/A | Getting Ready | Chris Oshelski | Evaluation & job description | Evaluation & ILP participation | Brooke and Chris need to work the logistics of this out and create the tool to record the information. "How will you meet your personal professional goal in the LSSU Employee Evaluation? | Have tool and process ready by July 1 for implementation for SY2021/22
|  | 25 | Create Position Manuals for LSSU CSO staff |  | Implementing | Chris Oshelski & Brooke Maciag | Tasks & input from staff | Updated job descriptions & evaluations |  | Becky/Jenny Reorganization | 21-22